## SprintPlan
SharePointPath | Project | Task | SubTask | Done | Priority | TimeEstimate | AdditionalNotes
Path should match the project path in the DataScienceProjects folder exactly (case-sensitive). Every time Project is filled in Path should be too. Use forward slashes. Path is relative to 'DataScienceProjects - General'. Do not include 'DataScienceProjects - General' and before in the path. Use / separator (not \). | Auto Generated from the basename of SharePointPath. | These are broader categories of what needs to be accomplished. Every project must have at least one task. If a task has SubTasks only the first row it appears in must be filled in. Every Task/SubTask needs a time estimate. Keep these short (≤ 85 characters) but informative. | A Task does not need to have any SubTasks but may have as many SubTasks as you want (typically 2 or more). Every Task/SubTask needs a time estimate. Keep these short (≤ 85 characters) but informative. Note that SubTask will be concatenated with Task and displayed as a task when you update your timesheet (Keep Task + SubTask ≤ 85 characters total). | Mark the cell with a lowercase 'x' when the Task/ SubTask is completed. | An integer from 1 (highest) to 5 (lowest). Priority can be assigned at the Task or SubTask level. Any missing priority will be filled down by the last value. | An numeric estimate of hours to complete each Task or SubTask (not a range input). Every row must be filled and may include half hour intervals. Sprint total: 0 hours (aim for 6.5 hours per each day of the sprint). | Optional, additional notes that you may want for yourself. For example, you might use this space to provide more details on Tasks and SubTasks.
Note on A1: On Windows you can right click the folder while holding shift, then select 'Copy as path'. For all users, consider copying to your clipboard than then using cl::pp() to copy a formated path to your clipboard that you can paste directly here.
Note on F1: There should be variability in the priority levels as this helps identify items to complete first and items that could be pushed back a sprint if time is running out. Product development and Data Science infastructure tasks are of higher priority. Additionally, projects that are of higher value and urgent are of higher priority.
Note on H1: You can hit Alt + Enter for carriage returns

## ExamplePlan
SharePointPath | Project | Task | SubTask | Done | Priority | TimeEstimate | AdditionalNotes
Path should match the project path in the DataScienceProjects folder exactly (case-sensitive). Every time Project is filled in Path should be too. Use forward slashes. Path is relative to 'DataScienceProjects - General'. Do not include 'DataScienceProjects - General' and before in the path. Use / separator (not \). | Auto Generated from the basename of SharePointPath. | These are broader categories of what needs to be accomplished. Every project must have at least one task. If a task has SubTasks only the first row it appears in must be filled in. Every Task/SubTask needs a time estimate. Keep these short (≤ 85 characters) but informative. | A Task does not need to have any SubTasks but may have as many SubTasks as you want (typically 2 or more). Every Task/SubTask needs a time estimate. Keep these short (≤ 85 characters) but informative. Note that SubTask will be concatenated with Task and displayed as a task when you update your timesheet (Keep Task + SubTask ≤ 85 characters total). | Mark the cell with a lowercase 'x' when the Task/ SubTask is completed. | An integer from 1 (highest) to 5 (lowest). Priority can be assigned at the Task or SubTask level. Any missing priority will be filled down by the last value. | An numeric estimate of hours to complete each Task or SubTask (not a range input). Every row must be filled and may include half hour intervals. Sprint total: 64.5 hours (aim for 6.5 hours per each day of the sprint). | Optional, additional notes that you may want for yourself. For example, you might use this space to provide more details on Tasks and SubTasks.
`Data_Science_Admin/About_Data_Science | About Data Science | Investigate Light Box package |  |  | 4 | 1.5
|  | MS Forms | Portfolio Project submission form [internal] | x | 1 | 2.5
|  |  | Project submission form [external] | x |  | 2.5
|  | Add Design section to Cheat Sheet |  |  | 1 | 2.5 | Sections: assessment, experiment, test idea app, data set up
|  | Website | Create Index page |  | 3 | 6 | Link to Project Request form
|  |  | Bookdown into website |  | 2 | 7
|  |  | Programatically send files to blob storage |  | 5 | 3
|  |  | Investigate potential for Azure storage |  | 5 | 3
|  | Sharepoint |  |  | 4 | 4 | Use as "checkpoint" to send reader to website/portfolio/Teams
|  | Dedicated Teams Channel |  |  | 4 | 1.5 | Communicate with stakeholders - Private? General?
Baseline/`Project_CEO_Projects/Project_CEO_Reliability | Project CEO Reliability | Planning |  |  | 5 | 4 | * Discuss with Steve * Research Reliability
|  | Clean data |  |  | 5 | 6
|  | Reliability analysis |  |  | 5 | 5
|  | Report writing & present results |  |  | 5 | 3
Business_Intelligence/Dashboards_Product_Detail | Dashboards Product Detail | Compliance Assist PowerBI dashboard: Filter for Outcomes Assessment Data Collection |  | x | 2 | 1
|  | Course Eval PowerBI dashboard: Investigate Closed Renewal total discrepancy |  |  | 2 | 4
|  | Engage PowerBI dashboard | Smart Pipeline feedback |  | 2 | 2
|  |  | Investigate why there is no 2021 data available |  |  | 4
`Data_Science_Admin/`Teaching_Learning/General_Professional_Development | General Professional Development | Python/PowerBI |  |  | 5 | 2
Note on A1: On Windows you can right click the folder while holding shift, then select 'Copy as path'. For all users, consider copying to your clipboard than then using cl::pp() to copy a formated path to your clipboard that you can paste directly here.
Note on F1: There should be variability in the priority levels as this helps identify items to complete first and items that could be pushed back a sprint if time is running out. Product development and Data Science infastructure tasks are of higher priority. Additionally, projects that are of higher value and urgent are of higher priority.
Note on H1: You can hit Alt + Enter for carriage returns
Note on C3: Tyler Rinker: Note the use of a link here to the DS Pipeline in a MS Planner board